## Project Timeline
|  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  |  | November
Item / Topic | Goal / Purpose of Meeting | Issues | Date | time axis 2023-02-05 to 2023-11-19
Form of Government |  |  | Feb / Mar | bar: 2023-02-05 to 2023-03-26
CRC Meeting | Manager/Mayor Panel - Gather input from government leaders and experts on form of government | Strong or weak Mayor elected city-wide vs. strong or weak City Manager appointed vs other structure; COO / CAO position; Election/appointment of Mayor if applicable | 2023-02-28 | bar: 2023-02-26
School Committee Meeting |  |  | 2023-03-14 | bar: 2023-03-12
CRC Meeting | current CM / recap of panel, summary of info gathered on mayor / manager / discussion of any additional info needed |  | 2023-03-14 | bar: 2023-03-12
City Council Meeting (report) | 3-5PM |  | 2023-03-22 | bar: 2023-03-19
CRC Meeting | target for working consensus on form of government |  | 2023-03-28 | bar: 2023-03-26
Legislative |  |  | April | bar: 2023-04-02 to 2023-04-30
CRC Meeting | summary of info gathered and discussion of info needed and various options / decisions (term, election of mayor) | At-large vs District Councilors or Combo, number of Councilors, term Limits (Councilors / Mayor), length of Term / Staggered Terms, goal Setting / Strategic Planning, Information sharing between branches of government, relationship between councilors and department heads, clarity on accountability and decision making, neighborhood Liaison, appointment Process - Department Heads / MMBS (filling, confirmation, vacancies, etc), vacancy Process, defined legislative process? | 2023-04-11 | bar: 2023-04-09
Public Hearing | Form of Government / City Council Structure / Terms / Responsibilities? | bar: 2023-04-16
CRC Meeting | target for working consensus on legislative structure |  | 2023-04-25 | bar: 2023-04-23
Executive |  |  | May | bar: 2023-05-07 to 2023-06-04
Term / Contract Limits on Mayor / Manager; Appointment Process Department Heads / MMBS (filling, confirmation, vacancies, etc); Required Dept Heads; Review of City Manager – Biennial; MMB Stipends; Administative Org
CRC Meeting | Present info on Executive Branch / Boards and Committees |  | 2023-05-09 | bar: 2023-05-07
CRC Meeting | Working consensus on Execuive Branch, Admin Org, Boards, Committees. |  | 2023-05-23 | bar: 2023-05-21
CRC Meeting | Draft lanague review |  | 2023-06-06 | bar: 2023-06-04
School Committee |  |  | June | bar: 2023-06-11 to 2023-06-18
Public Hearing | Executive Branch / School Committee / Department Heads & MMBS | At-large vs District School Committee Members Term Limits Length of Terms / Staggered Terms Vacancy Process | bar: 2023-06-11
CRC Meeting | Discussion and working consensus on School Committee |  | 2023-06-20 | bar: 2023-06-18
Elections |  |  | July | bar: 2023-06-25 to 2023-07-30
Election Year / Time of Year (odd vs even); Voter Eligibility - Under 18, non citizens, non residents; Distribution of Surplus; Method of Voting; Campaign Finance; Signature Requirements
CRC Meeting | Presentation of information and discussion |  | 2023-06-27 | bar: 2023-06-25
CRC Meeting |  |  | 2023-07-18 | bar: 2023-07-16
Discussion and working consensus on Elections
CRC Meeting | Draft lanague review |  | 2023-08-01 | bar: 2023-07-30
Finance and Budget |  |  | Aug | bar: 2023-08-13 to 2023-09-03
Non partisan CBO like group to.. ; City Auditor (election oversight?); Formalized CC budget priorities - early in budget process; Preservation of Financial Strength; Public Involvement in Budget Process
CRC Meeting | Presentation of information and discussion |  | 2023-08-15 | bar: 2023-08-13
CRC Meeting | Discussion and working consensus on Budget |  | 2023-08-29 | bar: 2023-08-27
Public Hearing | bar: 2023-09-03
Communications / Engagement / Participation Mechanisms |  |  | Sept | bar: 2023-09-10 to 2023-10-01
Town Meeting Style something.. ; Citizen Juries, Communication / Public Engagement Section of Charter, Participation Mechanims
CRC Meeting | Presentation of information and discussion |  | 2023-09-12 | bar: 2023-09-10
CRC Meeting | Discussion and working consensus on Communications end engagement provisions |  | 2023-09-26 | bar: 2023-09-24
Public Hearing | bar: 2023-10-01
Other / Revisit Topics |  |  | Oct | bar: 2023-10-08 to 2023-10-29
CRC Meeting | Discussion and working consensus on general and transition provisions | Preamble; Periodic Review of Ordinances/ MMBS; Definitions; Transition Provisions, General Provisions | 2023-10-10 | bar: 2023-10-08
CRC Meeting | Draft lanague review |  | 2023-10-24 | bar: 2023-10-22
Final Report |  |  | Nov | bar: 2023-11-05 to 2023-11-19
Public Hearing | bar: 2023-10-29
CRC Meeting | Review drafted language, make final edits and approve language |  | 2023-11-07 | bar: 2023-11-05
CRC Meeting | Review all final report materials and appendixes and approve |  | 2023-11-21 | bar: 2023-11-19

## Topics Questions
Themes
Form of Government | Information sharing between branches of government
Strong or weak Mayor elected city-wide vs. strong or weak City Manager appointed vs other structure | Removal of antiquated processes
COO / CAO position | Allow for more risk-taking and attempts at innovation
Election/appointment of Mayor if applicable | Can the charter increase the autonomy/flexibility of the City government (with regards
Preservation of what’s good/strong/working with current form
Themes
Enfranchisment / Equity (representation in government)
Participation / Accessibility
Legislative | Government Effectiveness / Collaboration
At-large vs District Councilors or Combo | Accountability / Responsiveness / Transparancy
Number of Councilors | Balance of Power
Term Limits (Councilors / Mayor)
Length of Term / Staggered Terms
Goal Setting / Strategic Planning
Information sharing between branches of government
Relationship between councilors and department heads
Clarity on accountibility and decision making
Neightborhood Liason ?
Appointment Process - Department Heads / MMBS (filling, confirmation, vacancies, etc)
Vacancy Process
Executive
Term / Contract Limits on Mayor / Manager
Appointment Process - Department Heads / MMBS (filling, confirmation, vacancies, etc)
Required Dept Heads?
Review of City Manager - Biennial
MMB Stipends
School Committee
At-large vs District School Committee Members
Term Limits
Length of Terms / Staggered Terms
Vacancy Process
Elections
Election Year / Time of Year (odd vs even)
Voter Eligibility - Under 18, non citizens, non residents
Distribution of Surplus
Method of Voting
Campaign Finance
Signature Requirements
Budget
Non partisain CBO like group to..
City Auditor (election oversight?)
Formalized CC budget priorities, early in budget process
Preservation of Financial Stength
Public Involvement in Budget Process
Participation Mechanisms / Other
Town Meeting Style something..
Citizen Juries
Communication / Public Engagement Section of Charter - PE department head, council committees with members of the public?
Preamble
Periodic Review of Ordinances/ MMBS
Definitions
Transition Provisions

## Questions
2. What was the law that had to be waived in the case of Boston to allow the city council to add as well as subtract from the proposed city budget? And how, if at all, does the existence of a Mayor rather than a City Manager affect this case?
Turnover rate in Cambridge
1. Is there an easily legible chart or other description of the charges of the various important committees, including how members are appointed or otherwise chosen?